SOLUTION REFERENCE REPORT

# C3 · 8D / PQM
Quality-Escalation Agent

Implementation blueprint for P3 Project No. 2, Wave 1, Rank 6

|  | Purpose Provide a durable reference for solution design, backlog definition, technical build, validation, deployment, governance and later productisation. |
| --- | --- |

| Portfolio | P3 |
| --- | --- |
| Starting asset | 04_P3_BW_IA_Agent_8D_PQM_Auditor |
| Priority / complexity | High / Medium |
| Status in tracker | Planned |
| Prepared for | P3 PMO, Quality, Data & AI delivery teams |
| Document date | 7 September 2026 |

Prepared by: Juan Eduardo Ramirez Millan

Reference baseline: AI_ML_Project_Tracker_Plan_2026-2027.xlsx

# Document control

| Field | Definition |
| --- | --- |
| Document owner | P3 AI / ML Portfolio PMO |
| Business owner | To be assigned at G0 |
| Product owner | To be assigned at G0 |
| Version | 1.0 |
| Classification | Internal working document |
| Review cycle | At each formal gate and after material architecture or scope change |
| Intended use | Reference for design, planning, build, validation, handover and productisation |

## How to use this report

Use Sections 1–4 to align sponsors, Quality and the delivery team on the product boundary and operating model.

Use Sections 5–8 as the functional and technical design baseline for epics, user stories and interface specifications.

Use Sections 9–12 for test design, PMO governance, gate reviews and release control.

Use the appendices as reusable checklists during case onboarding, validation and change control.

Treat all proposed targets and design choices as recommendations until formally approved at the applicable gate.

## Contents

1. Executive summary

2. Project context and objectives

3. Product scope and guiding principles

4. Target operating model

5. Functional capabilities

6. End-to-end process and approval gates

7. Information and data design

8. Technical architecture

9. AI, ML and evaluation strategy

10. Cockpit, KPIs and reporting

11. Delivery roadmap and gate criteria

12. Governance, security and risk controls

13. Productisation and support model

14. Decisions required and next actions

Appendices A–D

# 1. Executive summary

P3 should implement the rank-6 project as a human-controlled 8D/PQM quality-escalation product. The solution will assemble controlled evidence, prepare and challenge an 8D, verify that accepted lessons are reflected in PFMEA and Control Plan revisions, coordinate containment and escalation, and publish an operational cockpit. It will not autonomously approve root causes, change controlled quality documents, release product or close a customer case.

|  | Recommended product boundary Automate preparation, comparison, traceability and workflow. Preserve human accountability for technical validity, customer communication, document release and case closure. |
| --- | --- |

## 1.1 Business case

The project tracker identifies slow 8D preparation and weak evidence linkage.

The tracker states that corrective actions are not consistently incorporated into FMEA and Control Plan documents.

The tracker reports approximately 53% 8D on-time performance against a 75% target.

The existing starting asset reduces discovery and build effort, provided its contents pass G1 technical and governance review.

The capability can be reused across automotive customers using structured complaint handling, 8D, PFMEA and Control Plan governance.

## 1.2 Proposed success definition

| Outcome | Definition of success |
| --- | --- |
| Faster preparation | The agent produces an evidence-linked first draft and missing-information list for reviewer use. |
| Stronger quality | All material statements are traceable to approved evidence; facts, assumptions and hypotheses are visibly separated. |
| Closed learning loop | Accepted root causes and actions are demonstrably reflected in relevant controlled documents. |
| Disciplined execution | Each action has an owner, due date, evidence requirement, state and escalation rule. |
| Safe adoption | No external submission, root-cause approval, release decision or case closure occurs without authorised human approval. |
| Reusable product | Customer-specific templates, mappings, thresholds and roles are configuration rather than hard-coded logic. |

# 2. Project context and objectives

## 2.1 Tracker baseline

| Attribute | Tracker baseline |
| --- | --- |
| Project | C3 · 8D / PQM quality-escalation agent |
| Portfolio / wave / rank | P3 / Wave 1 / Rank 6 |
| Existing asset | 04_P3_BW_IA_Agent_8D_PQM_Auditor |
| Priority / complexity | High / Medium |
| Status | Planned |
| Expected output | Traceable 8D draft, missing-evidence questions, confirmed FMEA / Control Plan updates, containment plan and cockpit |
| Proposed tools | LLM/RAG, Python, controlled evidence repository, Sentence-BERT similarity and Power BI |

## 2.2 Objectives

Reduce avoidable administrative effort in complaint and PQM case preparation.

Improve completeness, consistency and traceability across D1–D8.

Separate occurrence cause, escape cause, systemic cause and supporting evidence.

Ensure approved corrective actions are carried into PFMEA, Control Plan and relevant work instructions.

Create forward-looking visibility of overdue actions, blocked decisions and cases at risk.

Build a controlled accelerator that P3 can configure for later customers.

## 2.3 Non-objectives for the first release

Autonomous approval of technical root cause or permanent corrective action.

Automatic product release, shipment release or change of EOL acceptance limits.

Unsupervised editing of official customer portals or controlled documents.

Advanced computer vision, predictive escape scoring or broad cross-plant standardisation.

Replacement of the official PQM, QMS, PLM or document-management system of record.

# 3. Product scope and guiding principles

## 3.1 In-scope capability blocks

| # | Capability | Primary output |
| --- | --- | --- |
| 1 | Case intake and PQM synchronisation | Structured case record with canonical identifiers |
| 2 | Controlled evidence workspace | Approved evidence set, revision status and source links |
| 3 | 8D drafting and challenge | D1–D8 draft plus completeness and consistency findings |
| 4 | PFMEA / Control Plan confirmation | Revision comparison and signed change-confirmation record |
| 5 | Containment and action workflow | Owner-assigned tasks, exit criteria, aging and escalation |
| 6 | Effectiveness and closure support | Evidence-based closure recommendation for human approval |
| 7 | Power BI cockpit | Executive, case, document-control and agent-quality views |
| 8 | Audit and monitoring | Immutable run, approval, source and version history |

## 3.2 Guiding principles

Evidence before narrative: The system must retrieve and validate evidence before generating conclusions.

Human approval by design: Approval states are enforced in the workflow and cannot be bypassed by prompt wording.

Deterministic controls around probabilistic AI: Identifiers, required fields, permissions, revisions and status transitions are validated by explicit rules.

Fail loud: Unresolved case ID, part number, revision, characteristic or source causes a review exception, never silent normalisation.

Configuration over custom code: Templates, thresholds, mappings, taxonomies and approval roles are externalised.

Measure business and model performance: The project measures on-time delivery, quality, effort, retrieval accuracy and unsafe-output prevention.

# 4. Target operating model

## 4.1 Case lifecycle

|  | Controlled state model New case → Evidence incomplete → Containment active → Root cause under validation → Corrective action approved → Effectiveness monitoring → Documents updated → Customer closure → Archived |
| --- | --- |

The agent may recommend a state transition, but the workflow service must verify required artefacts and authorised approvals before changing the official state.

## 4.2 RACI baseline

| Role | Accountability | Key approvals |
| --- | --- | --- |
| Customer quality lead | Own complaint and external communication | Case acceptance; customer submission; closure |
| 8D owner | Own D1–D8 content and timing | Draft completeness; root-cause package; final 8D |
| Process engineer | Validate technical cause and measures | Root cause; corrective action; effectiveness method |
| PFMEA moderator | Control PFMEA quality and release | PFMEA change |
| Control Plan owner | Control inspection and reaction-plan changes | Control Plan change |
| Production representative | Execute containment and actions | Execution evidence |
| PMO / PQM coordinator | Monitor aging, dependencies and escalation | Escalation package quality |
| P3 AI product owner | Own requirements, evaluation and release | Product gate recommendation |
| Data / AI engineer | Build and operate solution components | Technical evidence |
| IT / security owner | Control access, deployment and retention | Security and operational readiness |

## 4.3 Approval status labels

AI draft

Awaiting engineering validation

Approved for internal use

Approved for customer submission

Closed by authorised owner

# 5. Functional capabilities

## 5.1 Intake and evidence agent

Create or update a case workspace from an approved source.

Resolve case, part, plant, line, lot, DMC and serial identifiers.

Classify incoming evidence and identify duplicates or superseded revisions.

Produce a missing-evidence request list.

Maintain exact links to source documents and extracted passages.

## 5.2 8D drafting agent

Generate section-level drafts only from the approved evidence set.

Separate facts, assumptions, hypotheses and recommendations.

Prevent “confirmed root cause” language without validation evidence.

Maintain internal and customer-facing variants based on the same controlled facts.

Expose citations at field or statement level.

## 5.3 Root-cause challenge agent

Check that occurrence and escape root causes are separately addressed.

Challenge symptoms, circular logic and unsupported causal chains.

Compare Ishikawa, 5 Whys, tests and selected cause for consistency.

Keep alternative hypotheses open until discriminating evidence exists.

Request tests instead of inventing conclusions.

## 5.4 Containment and escalation agent

Propose containment boundaries using traceability evidence.

Create action candidates with owner, due date, dependency, evidence and exit criteria.

Track aging and blocked actions.

Recommend escalation using transparent rules.

Retain human approval before execution or external communication.

## 5.5 PFMEA and Control Plan auditor

Locate affected process step, function, failure mode, cause and control.

Compare old and new revisions and identify missing changes.

Check that prevention and detection controls address accepted causes.

Verify that approved changes appear in released revisions.

Create a signed change-confirmation record.

## 5.6 Effectiveness and closure agent

Request the agreed effectiveness evidence and observation period.

Compare post-action results with the approved baseline.

Detect recurrence or insufficient observation.

Prepare a closure recommendation.

Block autonomous closure.

# 6. End-to-end process and approval gates

| Stage | Agent contribution | Human control / exit evidence |
| --- | --- | --- |
| 1. Case initiation | Structure intake and identify missing identifiers | Quality lead accepts scope and affected product |
| 2. Evidence qualification | Classify, deduplicate and verify revisions | 8D owner approves evidence set |
| 3. Containment | Propose population, actions and exit criteria | Quality and production approve; execution evidence recorded |
| 4. Problem definition | Draft Is / Is Not and quantified D2 | 8D owner approves exact requirement, actual and boundary |
| 5. Cause analysis | Challenge hypotheses and evidence chain | Process engineer confirms occurrence and escape causes |
| 6. Corrective action | Link action to accepted cause and risk | Quality and process owner approve implementation |
| 7. Document feedback | Compare PFMEA / Control Plan revisions | Document owners approve and release changes |
| 8. Effectiveness | Monitor agreed indicators | 8D owner and customer quality accept evidence |
| 9. Closure | Compile final pack and lessons learned | Authorised customer or sponsor closes case |

## 6.1 Discipline acceptance checklist

| Discipline | Minimum controlled content |
| --- | --- |
| D1 | Named owner, discipline roles, required functions and approval authority |
| D2 | Failure, location, timing, affected population, requirement, actual result and evidence reference |
| D3 | Suspect population, inspection method, owner, start date, daily effectiveness and exit criteria |
| D4 | Technical and systemic occurrence / escape causes, validation evidence and alternatives considered |
| D5–D6 | Cause-linked actions, owner, due date, change risk, validation protocol and implementation evidence |
| D7 | PFMEA, Control Plan, work instruction, similar product / process, lessons learned and training applicability |
| D8 | Actions closed, effectiveness accepted, PQM reconciled, documents released and final approval archived |

# 7. Information and data design

## 7.1 Canonical entities

| Entity | Required examples |
| --- | --- |
| Quality case | Case ID, PQM number, 8D number, customer, status, owner and due dates |
| Product identity | Part number, drawing revision, DMC, serial, lot and production date |
| Failure | Failure mode, location, requirement, actual result, detection point and severity |
| Evidence item | Document type, revision, owner, approval state, source link, hash and access class |
| Cause hypothesis | Type, statement, status, supporting evidence, contrary evidence and approver |
| Action | Type, owner, due date, dependency, exit criterion, evidence and status |
| Controlled document | PFMEA / Control Plan / work instruction ID, revision, release status and changed rows |
| Approval | Decision, role, identity, timestamp, comment and version approved |
| Agent run | Model, prompt, tools, source set, output version, cost, latency and evaluation result |

## 7.2 Data-quality rules

No case evidence is used until the canonical case ID and access scope are resolved.

Only released controlled-document revisions can support closure confirmation.

Superseded documents remain traceable but are excluded from active recommendations.

Every generated material statement stores the source item and relevant passage or structured field.

Extraction confidence below the approved threshold routes the item to manual review.

Cross-customer and cross-case retrieval is prohibited unless explicitly approved and segregated.

## 7.3 Minimum evidence pack for pilot

Complaint or PQM record

Current 8D template and selected historical 8Ds

Failure photographs and measurement / test reports

Containment instructions and results

Relevant PFMEA and previous revision

Relevant Control Plan and previous revision

Action tracker and effectiveness evidence

Applicable internal procedure and customer submission format

# 8. Technical architecture

## 8.1 Logical architecture

| Layer | Responsibility |
| --- | --- |
| Experience layer | Case workspace, reviewer queue, approval screens and Power BI cockpit |
| Workflow layer | Case state machine, assignments, reminders, escalation and controlled write-back |
| Agent orchestration | Supervisor with specialised intake, drafting, challenge, document-diff and closure tools |
| Deterministic services | Schema validation, ID resolution, revision control, permissions, calculations and state checks |
| Knowledge services | Structured quality graph plus citation-enabled semantic retrieval |
| Data services | Relational case store, evidence metadata, object / document storage and audit log |
| Integration layer | Approved connectors for SharePoint, Teams / Outlook attachments, Excel trackers and PQM exports |
| Platform controls | Identity, RBAC, secrets, encryption, monitoring, version control, CI/CD and backup |

## 8.2 Reference processing flow

Ingest source item and preserve original link and metadata.

Resolve case scope, identifiers, document type, revision and approval state.

Extract text, tables and structured fields; quarantine low-confidence items.

Index approved content in the case-scoped retrieval service.

Invoke deterministic tools and specialised agents against a controlled source set.

Generate a draft with evidence links and explicit uncertainty labels.

Route the draft to the required approval role.

Write approved structured results through a schema-validating service.

Record source, version, approval and agent-run history in the audit log.

## 8.3 Recommended technology pattern

| Component | Recommended pattern |
| --- | --- |
| Controlled documents | Microsoft 365 / SharePoint or approved enterprise repository |
| Service layer | Python and API services for extraction, comparison and case logic |
| Structured store | Relational database for cases, actions, approvals and configuration |
| Semantic retrieval | Case-scoped vector index for historical evidence and procedures |
| Quality relationships | Graph or relational relationship model for defect–cause–control traceability |
| Workflow | Approval and notification workflow integrated with identity |
| Analytics | Power BI for executive, operational, document and agent-quality views |
| Identity and security | Enterprise identity, RBAC, managed secrets and encrypted transport / storage |
| Engineering operations | Version-controlled code, prompts, schemas, tests and deployment pipeline |

|  | Mandatory architecture constraint The LLM must not write directly to the official PQM record or controlled document. All write-back passes through deterministic schema, permission, revision and approval checks. |
| --- | --- |

# 9. AI, ML and evaluation strategy

## 9.1 AI use by maturity

| Maturity | Recommended use |
| --- | --- |
| Initial pilot | Retrieval, extraction, structured drafting, consistency challenge and document comparison |
| After controlled feedback | Ranking missing evidence, recommending similar cases and prioritising reviewer attention |
| After reliable labels | Supervised late-case risk, recurring failure patterns and root-cause candidate ranking |
| Explicitly excluded | Autonomous release, closure, engineering approval or EOL acceptance-limit decisions |

## 9.2 Evaluation set

Create a golden set of representative historical cases approved by Quality. Each case should contain the source evidence, expected structured fields, accepted causes, approved actions, released PFMEA / Control Plan changes and known pitfalls. Cases must be segregated by customer and access scope.

## 9.3 Evaluation dimensions

| Dimension | Example measure | Release expectation |
| --- | --- | --- |
| Extraction | Field accuracy for IDs, dates, measurements and revisions | Threshold approved at G1 |
| Retrieval | Relevant-source recall and wrong-case retrieval | Zero critical cross-case leakage |
| Grounding | Material statements with correct evidence | Proposed ≥95% citation coverage |
| Safety | Unsupported critical claims or blocked prohibited decisions | Zero critical unsafe outputs |
| Completeness | Mandatory 8D fields correctly identified | Proposed ≥95% before reviewer approval |
| Document feedback | Correct identification of required PFMEA / CP updates | 100% for pilot acceptance cases |
| Usability | Reviewer corrections, overrides and acceptance | Measured during G3 |
| Business impact | On-time rate and administrative effort | Compared with approved baseline |

The numerical thresholds above, except the tracker’s 53% baseline and 75% target, are proposed acceptance criteria and require approval at G1.

# 10. Cockpit, KPIs and reporting

## 10.1 Executive view

Open cases by severity and customer

8D on-time percentage

Cases at risk of missing the next deadline

Average and median aging

Containment overdue

Root cause not confirmed

Corrective action overdue

PFMEA / Control Plan confirmation missing

Cases awaiting customer closure

## 10.2 Case-control view

| Field group | Required content |
| --- | --- |
| Identity | PQM number, 8D number, customer, part and failure mode |
| Control | Severity, current discipline, owner, next milestone and days to due date |
| Evidence | Completeness, revision status and open requests |
| Execution | Containment, root cause, action and effectiveness states |
| Document loop | PFMEA, Control Plan and work-instruction update status |
| Escalation | Level, trigger, unresolved dependency and decision owner |

## 10.3 Agent-quality view

Drafts accepted without modification

Drafts accepted with modification

Unsupported-claim rate

Citation coverage

Wrong-document retrieval rate

Missing-field detection precision

Blocked unsafe outputs

Processing cost per case

User override rate

## 10.4 Pilot target framework

| KPI | Proposed target / control |
| --- | --- |
| 8D on-time performance | Recover to at least the tracker target of 75% |
| Statements with source evidence | ≥95% |
| Mandatory-field completeness before review | ≥95% |
| Approved PFMEA / CP changes with confirmation | 100% |
| Unsupported technical claims in customer draft | 0 critical |
| Administrative drafting effort | ≥40% reduction |
| Cases with named owner and next due date | 100% |
| Overdue critical actions surfaced | 100% |
| AI closure or release without approval | 0 |
| Wrong-customer or wrong-case retrieval | 0 critical |

# 11. Delivery roadmap and gate criteria

The dates below are taken from the attached tracker. Deliverables and exit criteria are the recommended implementation interpretation for this report.

| Gate | Tracker date | Reference deliverable |
| --- | --- | --- |
| Start | 7 Sep 2026 | Mobilisation and confirmed core team |
| G0 Project Definition | 14 Sep 2026 | Charter, use cases, RACI, baseline, acceptance criteria and RAID |
| G1 Technical Review | 16 Sep 2026 | Data access, canonical schema, architecture, evaluation set and control decisions |
| G2 Pilot Readiness | 30 Sep 2026 | End-to-end controlled pilot on real data with baseline |
| G3 Production Trial | 14 Oct 2026 | Shadow or assisted use with real quality users |
| G4 Customer Release | 28 Oct 2026 | Owner, runbook, support, security and production handover |
| G5 Productisation | 18 Nov 2026 | Configurable, reusable P3 product release |

## 11.1 Gate exit criteria

### G0

Named business and product owners

Agreed pilot cases and user group

Approved process boundary and KPI definitions

Initial risks, assumptions, issues and dependencies recorded

### G1

Source access and identifier strategy confirmed

Architecture and deployment approved

Security and data-classification review initiated or approved

Golden evaluation set defined

No unresolved blocker to case-level evidence segregation

### G2

MVP runs end to end on controlled customer data

Baseline recorded

No critical cross-case leakage or unsupported claim in acceptance set

Named quality user accepts the review workflow

### G3

Selected active cases processed in shadow or assisted mode

Corrections, overrides and failures logged

Weekly defect review operating

Support and incident paths exercised

### G4

Production workflow and access matrix approved

User and administrator runbooks complete

Rollback, retention and monitoring operational

Named customer owner and signed acceptance

### G5

Customer-specific mappings externalised

Reusable configuration package documented

Evaluation suite repeatable

Support and release model defined

## 11.2 Prioritised backlog

| Release | Scope |
| --- | --- |
| G2 must-have | Canonical IDs; intake; evidence classification; D2/D3 drafting; missing-evidence detection; cited retrieval; PFMEA/CP comparison; approval queue; basic cockpit; audit log |
| G3/G4 must-have | Full D1–D8 workflow; root-cause challenge; PQM reconciliation; action aging; effectiveness; customer template; RBAC; monitoring; training |
| G5 / later | Learned root-cause ranking; complaint clustering; cross-plant read-across; vision; late-case prediction; broad portal automation |

# 12. Governance, security and risk controls

## 12.1 Core control requirements

Case-level and customer-level access segregation.

Encryption in transit and at rest using approved enterprise controls.

Prompt, model, schema, configuration and knowledge-index version history.

Immutable source, draft, approval and write-back audit history.

Retention and deletion aligned with contractual and quality-record requirements.

Incident handling for data leakage, incorrect recommendations and unavailable service.

Monitoring of performance, drift, cost, access and policy violations.

Human override and rollback available at every operational stage.

## 12.2 Principal risks and mitigations

| Risk | Required mitigation |
| --- | --- |
| Hallucinated cause or action | Evidence-only generation, citations and engineering approval |
| Wrong case retrieved | Case/customer filters before semantic search and zero-tolerance leakage tests |
| Obsolete controlled document | Released-revision status check and explicit superseded-document handling |
| Poor scan or table extraction | Confidence threshold and manual review queue |
| AI recommendation treated as approval | Visible draft label and enforced state transition permissions |
| Action closed without effectiveness | Mandatory objective evidence and independent approval |
| User bypasses workflow | RBAC, immutable audit and blocked invalid transitions |
| Scope expansion delays release | Fixed G2 MVP and deferred backlog |
| Model or prompt change degrades quality | Versioned evaluation before promotion |
| Vendor or platform dependency | Approved architecture, exit path, data portability and monitored service controls |

## 12.3 Escalation rules

Use the portfolio rule from the tracker: a gate more than one week late is escalated at the weekly review and the slot is not reassigned until the gate is signed.

Immediately escalate any cross-customer data exposure, unauthorised write-back, critical unsupported claim, or product-release recommendation presented as an approval.

Escalate an active quality case when a critical action is overdue, containment lacks effectiveness evidence, a required decision owner is missing, or closure depends on an unreleased document revision.

Display the trigger, impact, decision required, accountable owner and latest acceptable decision date in every escalation package.

# 13. Productisation and support model

## 13.1 Configuration to externalise

Customer terminology and case taxonomy

8D and PQM templates

PQM field mappings and portal interfaces

Escalation thresholds and calendars

Evidence requirements by discipline

PFMEA / Control Plan schemas

Approval roles and segregation rules

Cockpit measures, filters and branding

Retention and support parameters

## 13.2 Support responsibilities

| Support layer | Responsibility |
| --- | --- |
| L1 user support | Access, workflow navigation, missing assignments and standard questions |
| L2 product support | Configuration, connector, extraction, cockpit and workflow defects |
| L3 engineering | Code, orchestration, model, retrieval, security and performance defects |
| Quality governance | Acceptance rules, templates, taxonomies and technical-content disputes |
| Product management | Roadmap, release decision, reuse package and customer-specific exceptions |

## 13.3 Release management

Every release includes code, prompt, schema, configuration and evaluation versions.

Promotion requires passing the approved regression set and security controls.

Material retrieval, model or prompt changes require documented impact assessment.

Rollback targets the complete product version, not only the model.

Customer-specific changes remain isolated and are promoted into the core product only after governance review.

# 14. Decisions required and next actions

| Priority | Decision / action | Owner | Gate |
| --- | --- | --- | --- |
| Critical | Confirm business owner, product owner and pilot quality lead | P3 sponsor / PMO | G0 |
| Critical | Approve pilot case population and accessible source systems | Quality + IT | G0/G1 |
| Critical | Decide system of record and write-back boundary | Quality + IT | G1 |
| Critical | Approve canonical identifiers and document revision rules | Quality data owner | G1 |
| High | Approve deployment, identity and evidence-storage architecture | IT / security | G1 |
| High | Approve golden evaluation set and critical-failure definitions | Quality + AI product owner | G1 |
| High | Confirm G2 MVP and defer out-of-scope features | Sponsor / product owner | G1 |
| High | Assign PFMEA and Control Plan approval roles | Quality management | G1 |
| Medium | Agree cockpit KPI definitions and baseline calculation | PMO / business owner | G2 |
| Medium | Define G3 trial users, cases and operating cadence | Product owner | G2 |

|  | Go / no-go principle Do not enter G2 build completion without reliable case identifiers, controlled revisions, approved access segregation and an agreed evaluation set. These are prerequisites for safe evidence-grounded automation. |
| --- | --- |

# Appendix A. Pilot acceptance checklist

| Control area | Acceptance evidence |
| --- | --- |
| Scope | Pilot users, cases, source systems and excluded decisions documented |
| Data | Canonical ID resolves correctly for every acceptance case |
| Security | Access segregation and approved service identities verified |
| Evidence | Sources retain original link, revision and approval state |
| Retrieval | No critical wrong-case or wrong-customer retrieval |
| Drafting | Facts, hypotheses and recommendations visibly separated |
| Grounding | Material statements link to correct supporting evidence |
| D4 control | Root cause cannot be labelled confirmed without approval evidence |
| Document loop | PFMEA and Control Plan changes correctly located and compared |
| Workflow | Required approver cannot be bypassed |
| Audit | Run, source, version, correction and approval history captured |
| Cockpit | KPIs reconcile to controlled case data |
| Operations | Monitoring, incident route and rollback demonstrated |
| Training | Pilot users understand draft labels and approval responsibilities |

# Appendix B. Minimum case data dictionary

| Field group | Minimum fields |
| --- | --- |
| Case identity | Case ID, PQM number, 8D number, customer, plant, owner and state |
| Product | Part number, drawing revision, variant, DMC, serial, lot and production date |
| Problem | Failure mode, requirement, actual, quantity, location, detection point and severity |
| Timing | Detection date, opening date, discipline due dates and closure date |
| Containment | Population, inspection method, owner, start, result and exit criteria |
| Cause | Occurrence/escape; technical/systemic; hypothesis status; evidence and approver |
| Action | Containment/corrective/preventive; owner; due date; dependency; evidence and status |
| Documents | Document ID, type, revision, release state, changed row / characteristic and link |
| Effectiveness | Metric, baseline, target, observation period, result and acceptance |
| AI trace | Source set, model, prompt, tools, output version, correction and final decision |

# Appendix C. User-story starter set

| ID | User story |
| --- | --- |
| US-01 | As an 8D owner, I want a new case workspace created from an approved PQM record so that all activities use one canonical identity. |
| US-02 | As a quality reviewer, I want missing mandatory evidence listed by discipline so that the team requests information before drafting conclusions. |
| US-03 | As a process engineer, I want each proposed root cause linked to supporting and contrary evidence so that confirmation is technically defensible. |
| US-04 | As a PFMEA moderator, I want the accepted cause mapped to the relevant PFMEA row so that missing prevention or detection changes are visible. |
| US-05 | As a Control Plan owner, I want old and new revisions compared at characteristic and reaction-plan level so that the released control reflects the approved action. |
| US-06 | As a PQM coordinator, I want overdue and blocked actions prioritised with transparent triggers so that escalation is timely. |
| US-07 | As a customer quality lead, I want an approved customer-facing draft generated from the same controlled facts so that communication is consistent. |
| US-08 | As a product owner, I want every agent output, source, correction and approval recorded so that the product can be audited and improved. |
| US-09 | As an administrator, I want customer-specific templates and thresholds configured without code changes so that the solution can be reused. |
| US-10 | As a release owner, I want promotion blocked when regression or safety tests fail so that product changes do not degrade control. |

# Appendix D. Source and assumption notes

## D.1 Source used

AI_ML_Project_Tracker_Plan_2026-2027.xlsx, provided by Juan Eduardo Ramirez Millan. The workbook supplies the project identity, rank, portfolio, starting asset, problem statement, proposed architecture, tools, expected outputs, priority, complexity, status, gate dates and portfolio escalation rule used in this report.

## D.2 Design recommendations introduced by this report

The operating model, roles, detailed workflow, canonical data model, architecture decomposition, evaluation framework, KPI proposals, controls, backlog interpretation, user stories and acceptance checklists are solution-design recommendations. They require confirmation through P3 governance and customer-specific technical, security, quality and contractual reviews.

## D.3 Change log

| Version | Date | Change | Author |
| --- | --- | --- | --- |
| 1.0 | 7 Sep 2026 | Initial solution reference report | Juan Eduardo Ramirez Millan / Microsoft 365 Copilot |